## Tabelle1
Github Ressource:
https://github.com/alexej-khalilzada/constructor-nukes.git
Meeting Room 1 |  | Topics | 2DOS |  | Results
chat room 1 | Mi
POSSIBLE TOPICS |  | Org | Get Things up and running (ALL) |  | Working NBs/ Connection
Nuke data | Meet | Infra | Input / Data Aggregation (inplace)
#NAME? |  | Define 1st Subgroups | Output / Main (remote)
#NAME?
POSSIBLE ANALYSIS
Timelines | 15:00 |  |  |  | 80%+ Datasources / 80%+ Plot Approaches/ Main template
Correlations | Meet | Requirements | Data - optimization
Careful predictions |  | Review - Artifacts | Output - optimization
World map app | 16:40 Review Ansam
Nuke-Tests | 17:00 |  |  |  | 95% Data available / easily usable
| Meet | Review - Artifacts / Discuss Plot Script Architecture
2DOS:
Data - aggregation | Do
Data - optimization | 9:00 | Open points/remarks
| Meet |  | Evaluation | Evaluation - description
Evaluation - description |  |  |  | Evaluation - statistics
Evaluation - statistics
| 14:00 |  |  |  | 80% Evaluation up and running
Plots | Meet | Requirements | MVP | Structure
Presentation |  | Review - Artifacts |  | Story
Slides
| 16:00 |  |  |  | 100% evaluation, 80% Slides
| Meet | Review - Artifacts
PLANNING
Fr
| 9:00 | Meet for Presentation | Presentation (All)
Meet
| 13:00 | Final review, deploy |  |  | 100% Slides + Presentation
_______________
14 - Deadline
16 - Presentation